Rezoning            	Application# 02-2024

1. Newspaper Ad PZAB (at least 10 7 days prior to public hearing) Newspaper ad sent by Feb 21, 2024 & in Newspaper by Feb 26, 2024
2. Signage (at least 5 business days prior to public hearing) Feb 26, 2024
3. Mailouts (at least 5 business days prior to public hearing) Feb 26, 2024
4. PZAB agenda deadline Novus Feb 28, 2024
5. PZAB Public Hearing March 7, 2024
6. Newspaper Ad for Village Council Public Hearing #1 – at least 7 days ahead of the hearing. Newspaper ad sent by February 23, 2024 & in Newspaper by February 29, 2024
7. Village Council agenda deadline date March 6, 2024
8. Village Council Public Hearing # 1 Mailouts March 7, 2024
9. Village Council Public Hearing # 1Signage March 7, 2024
10. Village Council Public Hearing # 1 March 14, 2024
11. Within 31 days after the State deem complete, the CPA becomes effective. June 30, 2024. (No need to wait for the comp plan amendment to become effective to adopt the rezoning.  Recommend that it be done concurrently, tracking with revised timeline for comp plan amendment.  See Sec. 163.3184(12), Fla. Stat. (“CONCURRENT ZONING.—At the request of an applicant, a local government shall consider an application for zoning changes that would be required to properly enact any proposed plan amendment transmitted pursuant to this section. Zoning changes approved by the local government are contingent upon the comprehensive plan or plan amendment transmitted becoming effective.”))
12. Village Council Public Hearing # 2 agenda deadline. July 3, 2024
13. Newspaper Ad for Public Hearing # 2 – Ad sent by June 25, 2024 & in newspaper by June 28, 2024
14. Village Council Public Hearing # 2 Mailouts, June 25, 2024
15. Village Council Public Hearing # 2 Signage, June 25, 2024
16. Village Council Public Hearing #2 July 11, 2024, for Zoning Adoption. 




